## Slide 1: Touch For Food January 15 Meeting
CloudNine

## Slide 2: Agenda
Retrospective on last few sprints
Recap of meeting with Dr. Constantinides
Stakeholder update (Pat and Mat)
Review of what's left (stories, defects, and doc)
  1 minute per defect for the reporting person to explain the defect

## Slide 3: Agenda
Schedule, deadlines and goals
Demos
Code reviews with branches (Ryan)
Unit testing (Mike)

## Slide 4: Agenda
General Issues
  Database backup, restore and test data
  Email/Google group chains
  Finders and mappers
  File/folder cleanup?
  Db in memory issue
  Commit issues
  Coding standards
  Exception class for non-active menu
  Deleting a menu_item that is associated to an order
Scrum update from each team member
Questions and comments

## Slide 5: Retrospective – Sprint 4

## Slide 6: Retrospective – Sprint 4

## Slide 7: Retrospective – Sprint 4

## Slide 8: Retrospective – Sprint 4
Sprint 4 velocity (story points): 18 story points
Cumulative velocity (story points): 31 story points
Average velocity (story points): 7.75 story points
Sprint 4 velocity (p-h): 124.2 person-hours
Cumulative velocity (p-h): 222.2 person-hours
Average velocity per sprint: 55.6 person-hours

## Slide 9: Retrospective – Sprint 4
Total person-hours budgeted to date: 2,898 ph
Total person-hours worked: 516.705 ph
Person-hours budgeted per sprint: 414 ph
Person-hours worked in Sprint 4: 209.98 ph

## Slide 10: Retrospective – Sprint 5

## Slide 11: Retrospective – Sprint 5

## Slide 12: Retrospective – Sprint 5

## Slide 13: Retrospective – Sprint 5
Sprint 5 velocity (story points): ?? story points
  6 story points for Sign In and Manage Tables
Cumulative velocity (story points): 31 story points
Average velocity (story points): ?? story points
  If completed, average would be 7.7 story points
Sprint 5 velocity (p-h): 24.25 person-hours
Cumulative velocity (p-h): 246.5 person-hours
Average velocity per sprint: 49.3 person-hours

## Slide 14: Retrospective – Sprint 5
Total person-hours budgeted to date: 3,312 ph
Total person-hours worked: 769 ph
Person-hours budgeted per sprint: 414 ph
Person-hours worked in Sprint 5: 252 ph

## Slide 15: Retrospective – Sprint 5
Look and Feel
Sign In
Manage Tables

## Slide 16: Meeting Recap w/ Dr. Constantinides

## Slide 17: Stakeholder Update
Dr. Grogono

## Slide 18: Scrum update
2 minutes each

## Slide 19: What’s left
Backlog

## Slide 20: UIR
Review parts
Assign parts

## Slide 21: UI Testing
Review parts
Assign parts

## Slide 22: Goals
Scoping out social aspect
Todo:
  Call waiter
  Customer Bill Management
  Toppings and Sides
  Implement discussed patterns
  Fix flow, ensure all closed stories work the way they should (data validation, etc.)
  Android mobile wrapper (iPhone if there is time)
Discuss the rest

## Slide 23: Schedule
Sprint 6
  Review each story, fix flow
  Implement patterns (Mapper, Finder)
  UIR
  Bugs & QA
  Call waiter
  Bill Management
  View Menu
Sprint 7
  Toppings and sides
  Bugs
  SAD
  Update docs to hand in

## Slide 24: Schedule
Sprint 8
  Android wrapper
  NFC & QR Code
  Bugs
  Other features TBD

## Slide 25: Code Review Demo

## Slide 26: Unit Testing Demo

## Slide 27: General Issues
Database backup, restore and test data
  Make sure that after you backup, try to restore on your machine and if possible, send it to one person to test before commit
  Cristian demos .bak
  Chris demos .sql

## Slide 28: General Issues
Process on closing bugs
  Reporting person reviews it
  If the reporting person is working on it, someone who has a good understanding of the bug should review it

## Slide 29: General Issues
Email/Google group chains
Finder and mappers
File/folder cleanup
Db in memory issue

## Slide 30: General Issues
Commit standards
  Make sure you test db .bak and .sql
  Run the application and test to make sure nothing broke
  If after updating, files are missing, show all files and include them
  Probably less of an issue if branches are being used
  Don’t commit web.config or any other useless files

## Slide 31: General Issues
Create bug to fix coding standards
Exception class for non-active menu (Mike)
Deleting a menu_item that is associated to an order (Mike)

## Slide 32: Questions?