## Slide 1: Touch For Food January 29 Meeting
CloudNine

## Slide 2: Agenda
Retrospective Sprint 6
UIR and Test Report
Stakeholder update
Meeting with Dr. Constantinides
Scrum updates w/ presentations
Goals
Schedule
General Issues

## Slide 3: Retrospective – Sprint 6

## Slide 4: Retrospective – Sprint 6

## Slide 5: Retrospective – Sprint 6

## Slide 6: Retrospective – Sprint 6
Sprint 6 velocity (story points): 11/4 story points
Cumulative velocity (story points): 87 story points
Average velocity (story points): 14.5 story points
Sprint 6 velocity (p-h): 223 person-hours
Cumulative velocity (p-h): 1,070 person-hours
Average velocity per sprint: 179 person-hours

## Slide 7: Retrospective – Sprint 6
Total person-hours budgeted to date: 3,726 ph
Total person-hours worked: 1,070 ph
Person-hours budgeted per sprint: 414 ph
Person-hours worked in Sprint 6: 223 ph

## Slide 8: Retrospective – Sprint 6
Please resolve any issues that are done but not yet closed
Log your time by Wednesday morning, February 30th
Don’t forget to log all your hours!

## Slide 9: UIR and Test Report
Updates?

## Slide 10: Stakeholder Update
Meeting with Dr. Grogono next Tuesday, February 5 (during our meeting time)
Must send him docs tomorrow (January 30)
Next meeting will be around one month later (beginning of March)

## Slide 11: Meeting with Dr. Constantinides
February 7
Will find out what needs to be prepared
Need to send him login for JIRA and Assembla
  How to handle these accounts?

## Slide 12: Scrum update w/ presentation
6 minutes each

## Slide 13: Scrum update w/ presentation
Sign in
Restaurant Bill Management
View Menu
Call Waiter
Bugs
Finders/Output Mappers
QA
Flow Fixing

## Slide 14: Goals
Todo:
  Finish search
  Finish call waiter
  Customer Bill Management
  Toppings and Sides
  Fix flow, ensure all closed stories work the way they should (data validation, etc.)
  Android mobile wrapper (iPhone if there is time)
  Reviews?
  See backlog for any new tasks/bugs added

## Slide 15: Schedule
Sprint 7
  SAD
  Update docs to hand in
  Finish Search
  Finish Call waiter
  QA
  Toppings and sides
  Fix flow
  Bugs
  User history/food reviews?

## Slide 16: Schedule
Sprint 8
  User history/food reviews
  Customer Bill Management
  Android wrapper
  NFC & QR Code
  Bugs
  QA
  Other features TBD

## Slide 17: General Issues
Pulling inactive or deleted data
Decision on how to pass error messages for feedback
Unit tests for Call Waiter
Number of code reviewers
  +1 or +2 needed to merge?

## Slide 18: General Issues
Code merge standards
  Merge trunk into branch first
  Time for merge demo?

## Slide 19: Questions?