## cumulative velocites vs time 1
Worst case | 0 | 150 | Cristian | 12.7 | Dates | 2012-10-22 | 0 | 0 | 0 | 0 | 6.5
Most Likely | 0 | 117 | Cynthia | 19.667 |  | 2012-10-23 | 11.5385 | 9 | 7.1538 | 9.1077 | 6.75
Best case | 0 | 93 | Josh | 32.5 |  | 2012-10-24 | 23.0769 | 18 | 14.3077 | 18.2154 | 6.75
Expected | 0 | 118.4 | Katrina | 11.75 |  | 2012-10-25 | 34.6154 | 27 | 21.4615 | 27.3231 | 10.75
Actual | 0 | 112.2 | Matthew | 7.25 |  | 2012-10-26 | 46.1538 | 36 | 28.6154 | 36.4308 | 24.533
|  |  | Mikhail | 6.833 |  | 2012-10-27 | 57.6923 | 45 | 35.7692 | 45.5385 | 35.95
|  |  | Patrick | 9.5 |  | 2012-10-28 | 69.2308 | 54 | 42.9231 | 54.6462 | 52.617
|  |  | Chris | 6.5 |  | 2012-10-29 | 80.7692 | 63 | 50.0769 | 63.7538 | 62.617
|  |  | Ryan | 5.5 |  | 2012-10-30 | 92.3077 | 72 | 57.2308 | 72.8615 | 62.617
[6 empty] | 2012-10-31 | 103.8462 | 81 | 64.3846 | 81.9692 | 65.534
[6 empty] | 2012-11-01 | 115.3846 | 90 | 71.5385 | 91.0769 | 69.784
[6 empty] | 2012-11-02 | 126.9231 | 99 | 78.6923 | 100.1846 | 73.784
[6 empty] | 2012-11-03 | 138.4615 | 108 | 85.8462 | 109.2923 | 91.534
[6 empty] | 2012-11-04 | 150 | 117 | 93 | 118.4 | 108.201

## time sheet for iteration 1
Reported? | Type | Key | Title | Date | Username | Time Spent (h) | Comment
| Sub-task | CAP-15 | CAP-14> Email | 2012-10-26 | Cynthia Donato | 0.25
| Sub-task | CAP-15 | CAP-14> Email | 2012-10-22 | Katrina Anderson | 0.5 | Read and wrote emails
| Sub-task | CAP-15 | CAP-14> Email | 2012-10-23 | Katrina Anderson | 0.25 | Read and wrote emails
| Sub-task | CAP-15 | CAP-14> Email | 2012-10-26 | Katrina Anderson | 0.25 | Read and wrote emails
| Sub-task | CAP-15 | CAP-14> Email | 2012-10-27 | Katrina Anderson | 1.5 | Read and wrote emails
| Sub-task | CAP-15 | CAP-14> Email | 2012-10-28 | Cynthia Donato | 0.5 | catching up on missed topics for setup
| Sub-task | CAP-15 | CAP-14> Email | 2012-10-27 | Patrick Modafferi | 1 | General Email plus SAD planning
| Sub-task | CAP-15 | CAP-14> Email | 2012-10-31 | Cynthia Donato | 0.5
| Sub-task | CAP-15 | CAP-14> Email | 2012-10-29 | Josh Hum | 6 | Agendas, planning emails, and discussions for the month of october
| Sub-task | CAP-15 | CAP-14> Email | 2012-11-04 | Josh Hum | 0.5 | group update request
| Sub-task | CAP-15 | CAP-14> Email | 2012-11-03 | Katrina Anderson | 1 | Read and Replied to emails.
| Sub-task | CAP-15 | CAP-14> Email | 2012-11-04 | Katrina Anderson | 0.5 | Read and replied to emails.
| Sub-task | CAP-44 | CAP-8> Test Plan | 2012-11-01 | Mikhail Levkovsky | 0.75 | worked on section 4,4.1 and 4.2.1
| Sub-task | CAP-44 | CAP-8> Test Plan | 2012-11-03 | Cynthia Donato | 0.75 | worked on section 4.2.2
| Sub-task | CAP-44 | CAP-8> Test Plan | 2012-11-02 | Katrina Anderson | 2 | Contributed Sections 5.1 & 5.2
| Sub-task | CAP-44 | CAP-8> Test Plan | 2012-11-03 | Katrina Anderson | 1 | Made corrections to document
| Sub-task | CAP-44 | CAP-8> Test Plan | 2012-11-01 | Josh Hum | 1.5 | Contributed Section 1
| Sub-task | CAP-44 | CAP-8> Test Plan | 2012-11-03 | Josh Hum | 0.25 | Reviewed Sections 4.1, 5.1 and 5.2
| Sub-task | CAP-44 | CAP-8> Test Plan | 2012-11-04 | Cynthia Donato | 0.25 | review section 4.2.3
| Sub-task | CAP-11 | CAP-8> SAD | 2012-10-26 | Mikhail Levkovsky | 1 | updated sad to contain sequence diagram for populate menu
| Sub-task | CAP-11 | CAP-8> SAD | 2012-10-26 | Patrick Modafferi | 2.5 | update Communication Diagrams for Manage menu
| Sub-task | CAP-59 | CAP-35> SAD 4.3 Login Page Use Case | 2012-11-03 | Matthew Tam | 0.5 | Wrote UC4.2 Login to Personal Profile
| Story | CAP-26 | View Menu | 2012-10-25 | Cristian Asenjo | 4 | Got things going by making a few custom views and trying (very unsuccessfully) to get custom routing and custom scaffolding to work.
| Story | CAP-26 | View Menu | 2012-10-26 | Cristian Asenjo | 0.867 | Added the menu_category custom view
| Sub-task | CAP-57 | CAP-8> Management Docs | 2012-10-27 | Katrina Anderson | 1 | Reviewed and fixed AHP document.
| Sub-task | CAP-57 | CAP-8> Management Docs | 2012-10-22 | Josh Hum | 5 | Worked on AHP.
| Sub-task | CAP-57 | CAP-8> Management Docs | 2012-11-03 | Josh Hum | 2 | Created outline for management docs
| Sub-task | CAP-56 | CAP-18> Other (Mini Team Meetings/Emergency Meetings/SCRUM) | 2012-10-22 | Katrina Anderson | 1 | Team 1 Google Talk Meeting about user story change.
| Sub-task | CAP-56 | CAP-18> Other (Mini Team Meetings/Emergency Meetings/SCRUM) | 2012-10-26 | Katrina Anderson | 1 | Emergency Meeting
| Sub-task | CAP-56 | CAP-18> Other (Mini Team Meetings/Emergency Meetings/SCRUM) | 2012-10-26 | Cristian Asenjo | 0.917 | Emergency meeting
| Sub-task | CAP-56 | CAP-18> Other (Mini Team Meetings/Emergency Meetings/SCRUM) | 2012-10-28 | Cristian Asenjo | 0.833 | Google Hangout conference call
| Sub-task | CAP-56 | CAP-18> Other (Mini Team Meetings/Emergency Meetings/SCRUM) | 2012-10-28 | Katrina Anderson | 0.833 | Google Hangout conference call
| Sub-task | CAP-56 | CAP-18> Other (Mini Team Meetings/Emergency Meetings/SCRUM) | 2012-10-28 | Cynthia Donato | 1 | West Island team meeting
| Sub-task | CAP-56 | CAP-18> Other (Mini Team Meetings/Emergency Meetings/SCRUM) | 2012-10-26 | Josh Hum | 1 | emergency meeting
| Sub-task | CAP-56 | CAP-18> Other (Mini Team Meetings/Emergency Meetings/SCRUM) | 2012-10-28 | Josh Hum | 0.75 | west island team meeting
| Sub-task | CAP-24 | CAP-8> Proposal | 2012-11-01 | Josh Hum | 0.5 | Rewrite and submit project description
| Task | CAP-8 | Documentation | 2012-11-03 | Mikhail Levkovsky | 0.5 | reviewing section 2.2 fixing refrences
| Task | CAP-23 | Setup | 2012-10-28 | Cynthia Donato | 1 | Setting up visual studio project and db
| Task | CAP-23 | Setup | 2012-10-28 | Cristian Asenjo | 0.5 | Updating Visual Studio with SP1 and the hotfix for the EMDX designer bug.
| Task | CAP-23 | Setup | 2012-10-31 | Cynthia Donato | 2 | installing service pack and hotfixes
| Task | CAP-23 | Setup | 2012-11-03 | Patrick Modafferi | 2 | installing SQL Manager. Trying to fix problem with rejected user when launching project
| Task | CAP-23 | Setup | 2012-11-02 | Patrick Modafferi | 2 | Trying to get SQL Manager 2008 R2 to work on windows 8 (still doesnt work)
| Bug | CAP-53 | DB structure for menu, item and category is faulty. | 2012-10-26 | Mikhail Levkovsky | 2
| Sub-task | CAP-66 | CAP-35> SAD 4.1 & 4.2 Update | 2012-11-04 | Josh Hum | 1 | Updated SAD 4.1 & 4.2
| Sub-task | CAP-65 | CAP-35> SAD 5.3 Class Diagram | 2012-11-04 | Cynthia Donato | 3 | remade diagram for mvc3
| Sub-task | CAP-64 | CAP-35> Customer Profile Page Programming | 2012-11-03 | Cynthia Donato | 0.5
| Sub-task | CAP-63 | CAP-35> SAD 4.3 Customer Sign-up Use Case | 2012-11-03 | Cristian Asenjo | 0.5 | Started and finished.
| Sub-task | CAP-62 | CAP-35> Customer Sign-up Page Programming | 2012-10-28 | Cristian Asenjo | 2 | Modified users table, figured out basic routing for custom URLs, added link to main page.
| Sub-task | CAP-62 | CAP-35> Customer Sign-up Page Programming | 2012-10-28 | Cristian Asenjo | 2 | Added validation for blank fields, added custom form page with proper labels.
| Sub-task | CAP-62 | CAP-35> Customer Sign-up Page Programming | 2012-10-29 | Cristian Asenjo | 1 | Re-did the page using the new project type
| Sub-task | CAP-61 | CAP-35> SAD 4.3 Customer Settings Page Use Case | 2012-10-31 | Cynthia Donato | 0.417
| Sub-task | CAP-60 | CAP-35> Customer Settings Page Programming | 2012-10-28 | Cynthia Donato | 2
| Sub-task | CAP-60 | CAP-35> Customer Settings Page Programming | 2012-11-03 | Cynthia Donato | 5.5
| Sub-task | CAP-19 | CAP-18> Weekly Group Meeting | 2012-10-28 | Matthew Tam | 0.75 | Attended Google Hangout for West Island Team - Meeting #1
| Sub-task | CAP-19 | CAP-18> Weekly Group Meeting | 2012-10-26 | Matthew Tam | 1 | Attended emergency group meeting
| Sub-task | CAP-19 | CAP-18> Weekly Group Meeting | 2012-10-29 | Cynthia Donato | 1
| Sub-task | CAP-19 | CAP-18> Weekly Group Meeting | 2012-10-26 | Patrick Modafferi | 2 | friday emergency meeting
| Sub-task | CAP-19 | CAP-18> Weekly Group Meeting | 2012-10-29 | Matthew Tam | 1 | Attended the weekly meeting
| Sub-task | CAP-19 | CAP-18> Weekly Group Meeting | 2012-10-29 | Josh Hum | 1 | Attended team meeting
| Task | CAP-18 | Meetings | 2012-10-26 | Cynthia Donato | 1 | Emergency meeting
| Sub-task | CAP-17 | CAP-14> Google Groups | 2012-10-27 | Cristian Asenjo | 0.083
| Sub-task | CAP-17 | CAP-14> Google Groups | 2012-11-03 | Mikhail Levkovsky | 0.583 | google group with patrick
| Sub-task | CAP-16 | CAP-14> Phone | 2012-10-27 | Katrina Anderson | 0.333 | Talked to Cynthia about group meetings and C3 design.
| Sub-task | CAP-16 | CAP-14> Phone | 2012-11-03 | Josh Hum | 1.5 | Phone calls with Katrina, Patrick and Mike over the past few weeks
| Sub-task | CAP-16 | CAP-14> Phone | 2012-11-03 | Josh Hum | 0.583 | Call with Katrina
| Sub-task | CAP-16 | CAP-14> Phone | 2012-11-03 | Katrina Anderson | 0.583 | Call with Josh
| Sub-task | CAP-16 | CAP-14> Phone | 2012-11-04 | Josh Hum | 0.083 | Phone call with Patrick
| Sub-task | CAP-16 | CAP-14> Phone | 2012-11-04 | Josh Hum | 0.333 | Call with Mike
| Sub-task | CAP-47 | CAP-27> Menu Editor Main Page | 2012-11-01 | Mikhail Levkovsky | 1.5 | started making the menu editor main page
| Sub-task | CAP-47 | CAP-27> Menu Editor Main Page | 2012-11-04 | Mikhail Levkovsky | 0.5 | updates to drop down list

## cumulative velocites vs time 2
Worst case | 0 | 170 | Cristian | 10 | Dates | 2012-11-06 | 0 | 0 | 0 | 0 | 3.416
Most Likely | 0 | 130 | Cynthia | 7.75 |  | 2012-11-07 | 11.3333 | 8.6667 | 7 | 8.8267 | 7.082
Best case | 0 | 105 | Josh | 9.41 |  | 2012-11-08 | 22.6667 | 17.3333 | 14 | 17.6533 | 7.665
Expected | 0 | 132.4 | Katrina | 18.91 |  | 2012-11-09 | 34 | 26 | 21 | 26.48 | 10.165
Actual | 0 | 118.75 | Matthew | 7.41 |  | 2012-11-10 | 45.3333 | 34.6667 | 28 | 35.3067 | 17.748
|  |  | Mikhail | 16.58 |  | 2012-11-11 | 56.6667 | 43.3333 | 35 | 44.1333 | 57.749
|  |  | Patrick | 23.25 |  | 2012-11-12 | 68 | 52 | 42 | 52.96 | 59.082
|  |  | Chris | 10 |  | 2012-11-13 | 79.3333 | 60.6667 | 49 | 61.7867 | 67.415
|  |  | Ryan | 8.5 |  | 2012-11-14 | 90.6667 | 69.3333 | 56 | 70.6133 | 77.415
[6 empty] | 2012-11-15 | 102 | 78 | 63 | 79.44 | 77.415
[6 empty] | 2012-11-16 | 113.3333 | 86.6667 | 70 | 88.2667 | 79.498
[6 empty] | 2012-11-17 | 124.6667 | 95.3333 | 77 | 97.0933 | 97.748
[6 empty] | 2012-11-18 | 136 | 104 | 84 | 105.92 | 104.832
[6 empty] | 2012-11-19 | 147.3333 | 112.6667 | 91 | 114.7467 | 112.832
[6 empty] | 2012-11-20 | 158.6667 | 121.3333 | 98 | 123.5733 | 118.832
[6 empty] | 2012-11-21 | 170 | 130 | 105 | 132.4 | 118.832

## time sheet for iteration 2
Reported? | Type | Key | Title | Date | Username | Time Spent (h) | Comment
| Task | CAP-23 | Setup | 2012-11-06 | Patrick Modafferi | 2 | Setting up the Sprint 2
| Bug | CAP-77 | Restaurants are not connected to any user | 2012-11-06 | Mikhail Levkovsky | 0.5
| Task | CAP-14 | Correspondence | 2012-11-06 | Mikhail Levkovsky | 0.083 | nice conversation with cristian
| Task | CAP-14 | Correspondence | 2012-11-06 | Cristian Asenjo | 0.083
| Task | CAP-14 | Correspondence | 2012-11-06 | Josh Hum | 0.75 | Emails for the sprint
| Task | CAP-23 | Setup | 2012-11-07 | Patrick Modafferi | 2 | Research and test on JIRA sprint functionality in Classic Mode
| Task | CAP-14 | Correspondence | 2012-11-07 | Cynthia Donato | 0.083
| Story | CAP-27 | Manage Menu | 2012-11-07 | Patrick Modafferi | 1 | TEST
| Task | CAP-14 | Correspondence | 2012-11-08 | Katrina Anderson | 0.5 | Read and wrote emails
| Task | CAP-14 | Correspondence | 2012-11-08 | Cynthia Donato | 0.083
| Task | CAP-23 | Setup | 2012-11-09 | Patrick Modafferi | 0.5 | Setting up filters and clean up for JIRA in general
| Task | CAP-14 | Correspondence | 2012-11-09 | Patrick Modafferi | 1 | Weekly email update + Emails for the week of Nov - 5
| Task | CAP-14 | Correspondence | 2012-11-09 | Cynthia Donato | 0.5
| Task | CAP-14 | Correspondence | 2012-11-09 | Matthew Tam | 0.5 | Accumulation of Weekly Emails
| Task | CAP-14 | Correspondence | 2012-11-10 | Cynthia Donato | 0.083
| Story | CAP-35 | Manage Personal Profile | 2012-11-10 | Cristian Asenjo | 2 | Unit testing for the UserController class
| Story | CAP-35 | Manage Personal Profile | 2012-11-10 | Cristian Asenjo | 0.5 | More work trying to get the Create method to test properly.
| Bug | CAP-83 | Confirm password entry isn't working after moving to a well-partial'd class | 2012-11-10 | Cristian Asenjo | 2 | Had to change the way we were using a custom class to add annotations, added extra fields and changed namespaces around.
| Bug | CAP-82 | Duplicate usernames can be created. Database has to be changed to restrict usernames to be unique. | 2012-11-10 | Cristian Asenjo | 3 | Validation works much better now.
| Task | CAP-23 | Setup | 2012-11-11 | Patrick Modafferi | 1.5 | got the project to work on Windows 8, FINALLY!
| Task | CAP-23 | Setup | 2012-11-11 | Katrina Anderson | 5 | Environment set up
| Task | CAP-18 | Meetings | 2012-11-11 | Matthew Tam | 0.667 | West Island Meeting #2
| Task | CAP-18 | Meetings | 2012-11-11 | Katrina Anderson | 0.667 | West Island Meeting #2
| Task | CAP-18 | Meetings | 2012-11-11 | Ryan Nasr | 4
| Task | CAP-18 | Meetings | 2012-11-11 | Christian Daher | 4
| Task | CAP-18 | Meetings | 2012-11-11 | Cristian Asenjo | 0.5 | West Island team hangout.
| Task | CAP-18 | Meetings | 2012-11-11 | Cristian Asenjo | 0.5 | Helping Matt with the dev environment.
| Task | CAP-18 | Meetings | 2012-11-11 | Cynthia Donato | 0.5 | West Island Team Meeting
| Task | CAP-18 | Meetings | 2012-11-11 | Josh Hum | 0.667 | West Island Meeting #2
| Task | CAP-14 | Correspondence | 2012-11-11 | Patrick Modafferi | 1 | emails for the week of nov 11
| Story | CAP-35 | Manage Personal Profile | 2012-11-11 | Cristian Asenjo | 2.5 | Past reviews now display when looking at a user's details
| Story | CAP-35 | Manage Personal Profile | 2012-11-11 | Cristian Asenjo | 0.5 | Adding the extra stuff to the DB
| Story | CAP-35 | Manage Personal Profile | 2012-11-11 | Matthew Tam | 4 | Added a LogOn View and added the logic in UserController
| Story | CAP-27 | Manage Menu | 2012-11-11 | Patrick Modafferi | 0.5
| Story | CAP-27 | Manage Menu | 2012-11-11 | Patrick Modafferi | 1 | Working on the flow
| Story | CAP-27 | Manage Menu | 2012-11-11 | Mikhail Levkovsky | 1
| Story | CAP-27 | Manage Menu | 2012-11-11 | Mikhail Levkovsky | 0.5
| Story | CAP-27 | Manage Menu | 2012-11-11 | Mikhail Levkovsky | 6.5 | worked on accessing the menu categories from within the menu list.
| Story | CAP-27 | Manage Menu | 2012-11-11 | Patrick Modafferi | 4.5 | Working on managing the categories, the flow of the management system and got removing menu_categories from a menu to work
| Story | CAP-37 | View Restaurant Statistics and Reviews | 2012-11-12 | Cristian Asenjo | 1.333 | Modified the database columns pertaining to ratings and wrote an SQL trigger to automatically update a restaurant's average rating.
| Task | CAP-23 | Setup | 2012-11-13 | Patrick Modafferi | 1 | More problems with JIRA and the sprint charts. Now figured out to set the start date to something.
| Task | CAP-23 | Setup | 2012-11-13 | Christian Daher | 2 | Setting up environment
| Task | CAP-14 | Correspondence | 2012-11-13 | Cynthia Donato | 0.083
| Story | CAP-27 | Manage Menu | 2012-11-13 | Mikhail Levkovsky | 2.5 | Included a partial view for category list and render it in the details of a menu.
| Story | CAP-27 | Manage Menu | 2012-11-13 | Patrick Modafferi | 1.5 | working on deleting and on displaying a list of available categories to add to the menu
| Story | CAP-27 | Manage Menu | 2012-11-13 | Mikhail Levkovsky | 1
| Story | CAP-27 | Manage Menu | 2012-11-13 | Matthew Tam | 0.25 | Provided some assistance with displaying the list of categories through a partial view
| Task | CAP-23 | Setup | 2012-11-14 | Josh Hum | 6 | setup visual studio, db, project, etc
| Story | CAP-39 | Leave Review | 2012-11-14 | Cristian Asenjo | 3 | Basic functionality complete, will mark as resolved and create bugs about the small details that are missing or need tweaking.
| Story | CAP-37 | View Restaurant Statistics and Reviews | 2012-11-14 | Cristian Asenjo | 1 | Past reviews can now be seen.
| Task | CAP-14 | Correspondence | 2012-11-16 | Cynthia Donato | 0.083
| Task | CAP-14 | Correspondence | 2012-11-16 | Matthew Tam | 0.5 | Accumulation of Weekly Emails
| Story | CAP-27 | Manage Menu | 2012-11-16 | Mikhail Levkovsky | 1.5 | added a utility class to factor out some common functionality.
| Task | CAP-23 | Setup | 2012-11-17 | Katrina Anderson | 10 | Environment set up
| Task | CAP-14 | Correspondence | 2012-11-17 | Cynthia Donato | 1 | Split section with Katrina
| Task | CAP-14 | Correspondence | 2012-11-17 | Katrina Anderson | 1 | Split section with Cynthia
| Story | CAP-27 | Manage Menu | 2012-11-17 | Patrick Modafferi | 1 | Locally testing the code visually
| Story | CAP-27 | Manage Menu | 2012-11-17 | Mikhail Levkovsky | 1 | acceptance testing locally
| Story | CAP-27 | Manage Menu | 2012-11-17 | Patrick Modafferi | 0.25 | Generating the item related views and controllers
| Story | CAP-26 | View Menu | 2012-11-17 | Christian Daher | 1 | Worked on View menu that displays all the categories. Waiting for the items crud to be able to work on the items view within the menu
| Story | CAP-26 | View Menu | 2012-11-17 | Christian Daher | 1 | View menu basics are done, tested it with a template item that i injected into the db, works great
| Story | CAP-26 | View Menu | 2012-11-17 | Ryan Nasr | 2
| Task | CAP-23 | Setup | 2012-11-18 | Ryan Nasr | 1 | Setup a central server database for the whole team to access.
| Task | CAP-14 | Correspondence | 2012-11-18 | Cynthia Donato | 0.25 | Read emails
| Task | CAP-14 | Correspondence | 2012-11-18 | Cynthia Donato | 0.167 | Text Mike
| Task | CAP-14 | Correspondence | 2012-11-18 | Cynthia Donato | 0.167 | Text Cristian
| Task | CAP-14 | Correspondence | 2012-11-18 | Cynthia Donato | 0.25 | Text Katrina
| Task | CAP-14 | Correspondence | 2012-11-18 | Cynthia Donato | 0.5 | Call Kat
| Task | CAP-14 | Correspondence | 2012-11-18 | Katrina Anderson | 0.75 | Phone call and texting with Cynthia
| Task | CAP-8 | Documentation | 2012-11-18 | Katrina Anderson | 1 | Document formatting and addition of use case.
| Story | CAP-35 | Manage Personal Profile | 2012-11-18 | Cynthia Donato | 3 | Added Past order view to user details page
| Task | CAP-23 | Setup | 2012-11-19 | Patrick Modafferi | 1 | retrieve all feedback and transfer into bugs
| Task | CAP-18 | Meetings | 2012-11-19 | Patrick Modafferi | 1.5 | Weekly Meeting about sprint 2 and discuss feedback from sprint 1
| Task | CAP-18 | Meetings | 2012-11-19 | Ryan Nasr | 1.5
| Task | CAP-18 | Meetings | 2012-11-19 | Matthew Tam | 1.5 | Weekly Meeting, discussed sprint 2
| Task | CAP-18 | Meetings | 2012-11-19 | Josh Hum | 2 | weekly meeting
| Task | CAP-14 | Correspondence | 2012-11-19 | Patrick Modafferi | 1 | Email about bug summary, email about JIRA and JIRA demo
| Story | CAP-35 | Manage Personal Profile | 2012-11-19 | Cynthia Donato | 1 | Added Order Details as a partial view to orders
| Task | CAP-23 | Setup | 2012-11-20 | Patrick Modafferi | 1 | set up Sprint 3 for JIRA
| Task | CAP-18 | Meetings | 2012-11-20 | Christian Daher | 2 | meeting
| Task | CAP-18 | Meetings | 2012-11-20 | Mikhail Levkovsky | 2
Helped debug installation issues
Cynthia helped me debug installation issues
added order details link to past orders
what is left to do, is a graceful removal of menu categories and a graceful addition of them.
figure out how to do proper ajax calls for the deletion and such... the ajax link seems a bit sketchy :s
Also, made a method that filters the list of categories in the CategoryController.
Gracefully deletes existing menu category items
also gave up on the ajax of adding and removing rows from a table (i.e. if you add a category to a menu it should delete from the category list and add it to the menu list).
still an ajax call but just refreshes page