## Sprint11
Test ID | Title | Environment | Sprint | Test Date | Status | Notes
TC025.1 | Test Create Order | Google Chrome - 26.0.1410.43 m | 6 | 2013-04-03 | PASS
TC026.1 | Test View Menu (Customer) | Google Chrome - 26.0.1410.43 m | 6 | 2013-04-03 | PASS
TC026.2 | Test View Menu (Restaurant) | Google Chrome - 26.0.1410.43 m | 6 | 2013-04-03 | PASS
TC026.3 | Test View Menu (Administrator) | Google Chrome - 26.0.1410.43 m | 6 | 2013-04-03 | PASS
TC026.4 | Test Search Menu (Customer) | Google Chrome - 26.0.1410.43 m | 8 | 2013-04-03 | PASS
TC026.5 | Test Search Menu (Restaurant) | Google Chrome - 26.0.1410.43 m | 8 | 2013-04-03 | PASS
TC027.1 | Test Menu Editor Main Page | Google Chrome - 26.0.1410.43 m | 6 | 2013-04-03 | PASS
TC027.2 | Test Category Management Page | Google Chrome - 26.0.1410.43 m | 6 | 2013-04-03 | PASS
TC027.3 | Test Item Management Page | Google Chrome - 26.0.1410.43 m | 6 | 2013-04-03 | PASS
TC027.4 | Test Menu Edit | Google Chrome - 26.0.1410.43 m | 6 | 2013-04-03 | PASS
TC027.5 | Test Create Menu | Google Chrome - 26.0.1410.43 m | 6 | 2013-04-03 | PASS
TC029.1 | Test Cancel Order | Google Chrome - 26.0.1410.43 m | 6 | 2013-04-03 | PASS | After confirming the canceling of an order it redirects you the login page.
TC029.2 | Test Decline Order Item | Google Chrome - 26.0.1410.43 m | 6 | 2013-04-03 | PASS
TC029.3 | Test Accept Order Item | Google Chrome - 26.0.1410.43 m | 6 | 2013-04-03 | PASS
TC034.1 | Test Create Service Request (Administrator) | Google Chrome - 26.0.1410.43 m | 7 | 2013-04-03 | PASS
TC034.2 | Test Create Service Request (Restaurant) | Google Chrome - 26.0.1410.43 m | 7 | 2013-04-03 | PASS
TC034.3 | Test Call Waiter (Customer) | Google Chrome - 26.0.1410.43 m | 7 | 2013-04-03 | PASS
TC034.4 | Test Edit Service Request (Restaurant) | Google Chrome - 26.0.1410.43 m | 7 | 2013-04-03 | PASS | Shouldn't be able to edit after it has been completed.
TC034.5 | Test Edit Service Request (Administrator) | Google Chrome - 26.0.1410.43 m | 7 | 2013-04-03 | PASS
TC034.6 | Test Cancel Service Request | Google Chrome - 26.0.1410.43 m | 7 | 2013-04-03 | PASS
TC034.7 | Test Complete Service Request | Google Chrome - 26.0.1410.43 m | 7 | 2013-04-03 | PASS
TC035.3 | Test Update Customer Settings | Google Chrome - 26.0.1410.43 m | 9 | 2013-04-03 | PASS
TC039.1 | Test Leave Review | Google Chrome - 26.0.1410.43 m | 8 | 2013-04-03 | PASS
TC039.2 | Test View Review | Google Chrome - 26.0.1410.43 m | 8 | 2013-04-03 | PASS
TC040.1 | Test Login With Non-Existent User | Google Chrome - 26.0.1410.43 m | 6 | 2013-04-03 | PASS
TC040.2 | Test Create New User | Google Chrome - 26.0.1410.43 m | 6 | 2013-04-03 | PASS
TC040.3 | Test Login With Existent User | Google Chrome - 26.0.1410.43 m | 6 | 2013-04-03 | PASS
TC040.4 | Test Logout | Google Chrome - 26.0.1410.43 m | 6 | 2013-04-03 | PASS
TC41.1 | Test Create Bill (Customer) | Google Chrome - 26.0.1410.43 m | 8 | 2013-04-03 | PASS | You can create as many bills as you want as a user.
TC41.2 | Test Add Item to Bill (Customer) | Google Chrome - 26.0.1410.43 m | 8 | 2013-04-03 | PASS
TC41.3 | Test Remove Item From Bill (Customer) | Google Chrome - 26.0.1410.43 m | 9 | 2013-04-03 | PASS
TC41.4 | Test Delete Bill (Customer) | Google Chrome - 26.0.1410.43 m | 9 | 2013-04-03 | PASS
TC42.1 | Test Create Bill (Restaurant) | Google Chrome - 26.0.1410.43 m | 7 | 2013-04-03 | PASS
TC42.2 | Test Add Item to Bill (Restaurant) | Google Chrome - 26.0.1410.43 m | 7 | 2013-04-03 | PASS
TC42.3 | Test Remove Item from Bill (Restaurant) | Google Chrome - 26.0.1410.43 m | 7 | 2013-04-03 | PASS
TC42.4 | Test Delete Bill (Restaurant) | Google Chrome - 26.0.1410.43 m | 7 | 2013-04-03 | PASS
TC192.1 | Test Create Table Page | Google Chrome - 26.0.1410.43 m | 6 | 2013-04-03 | PASS
TC192.2 | Test Creating Incorrect Table Page | Google Chrome - 26.0.1410.43 m | 6 | 2013-04-03 | PASS
TC192.3 | Test Edit Table Page | Google Chrome - 26.0.1410.43 m | 6 | 2013-04-03 | PASS
TC192.4 | Test Incorrect Edit Table Page | Google Chrome - 26.0.1410.43 m | 6 | 2013-04-03 | PASS
TC192.5 | Test NFC Link Page | Google Chrome - 26.0.1410.43 m | 6 | 2013-04-03 | PASS
TC192.6 | Test Table Details Page | Google Chrome - 26.0.1410.43 m | 6 | 2013-04-03 | PASS
TC192.7 | Test Delete Table Page | Google Chrome - 26.0.1410.43 m | 6 | 2013-04-03 | PASS
TC279.1 | Test View Past Orders | Google Chrome - 26.0.1410.43 m | 8 | 2013-04-03 | PASS
TC279.2 | Test Suggest an Order | Google Chrome - 26.0.1410.43 m | 8 | 2013-04-03 | PASS

## Sprint11-Android
Test ID | Title | Environment | Sprint | Test Date | Status | Notes
TC025.1 | Test Create Order | Samsung S3 - Android 4.1.1 | 6 | 2013-04-03 | PASS
TC026.1 | Test View Menu (Customer) | Samsung S3 - Android 4.1.2 | 6 | 2013-04-03 | PASS
TC026.2 | Test View Menu (Restaurant) | Samsung S3 - Android 4.1.3 | 6 | 2013-04-03 | N/A
TC026.3 | Test View Menu (Administrator) | Samsung S3 - Android 4.1.4 | 6 | 2013-04-03 | N/A
TC026.4 | Test Search Menu (Customer) | Samsung S3 - Android 4.1.5 | 8 | 2013-04-03 | PASS
TC026.5 | Test Search Menu (Restaurant) | Samsung S3 - Android 4.1.6 | 8 | 2013-04-03 | N/A
TC027.1 | Test Menu Editor Main Page | Samsung S3 - Android 4.1.8 | 6 | 2013-04-03 | N/A
TC027.2 | Test Category Management Page | Samsung S3 - Android 4.1.9 | 6 | 2013-04-03 | N/A
TC027.3 | Test Item Management Page | Samsung S3 - Android 4.1.10 | 6 | 2013-04-03 | N/A
TC027.4 | Test Menu Edit | Samsung S3 - Android 4.1.11 | 6 | 2013-04-03 | N/A
TC027.5 | Test Create Menu | Samsung S3 - Android 4.1.12 | 6 | 2013-04-03 | N/A
TC029.1 | Test Cancel Order | Samsung S3 - Android 4.1.13 | 6 | 2013-04-03 | N/A
TC029.2 | Test Decline Order Item | Samsung S3 - Android 4.1.14 | 6 | 2013-04-03 | N/A
TC029.3 | Test Accept Order Item | Samsung S3 - Android 4.1.15 | 6 | 2013-04-03 | N/A
TC034.1 | Test Create Service Request (Administrator) | Samsung S3 - Android 4.1.16 | 7 | 2013-04-03 | N/A
TC034.2 | Test Create Service Request (Restaurant) | Samsung S3 - Android 4.1.17 | 7 | 2013-04-03 | N/A
TC034.3 | Test Call Waiter (Customer) | Samsung S3 - Android 4.1.18 | 7 | 2013-04-03 | PASS
TC034.4 | Test Edit Service Request (Restaurant) | Samsung S3 - Android 4.1.19 | 7 | 2013-04-03 | N/A
TC034.5 | Test Edit Service Request (Administrator) | Samsung S3 - Android 4.1.20 | 7 | 2013-04-03 | N/A
TC034.6 | Test Cancel Service Request | Samsung S3 - Android 4.1.21 | 7 | 2013-04-03 | N/A
TC034.7 | Test Complete Service Request | Samsung S3 - Android 4.1.22 | 7 | 2013-04-03 | N/A
TC035.3 | Test Update Customer Settings | Samsung S3 - Android 4.1.23 | 9 | 2013-04-03 | PASS
TC039.1 | Test Leave Review | Samsung S3 - Android 4.1.24 | 8 | 2013-04-03 | PASS
TC039.2 | Test View Review | Samsung S3 - Android 4.1.25 | 8 | 2013-04-03 | PASS
TC040.1 | Test Login With Non-Existent User | Samsung S3 - Android 4.1.26 | 6 | 2013-04-03 | PASS
TC040.2 | Test Create New User | Samsung S3 - Android 4.1.27 | 6 | 2013-04-03 | PASS
TC040.3 | Test Login With Existent User | Samsung S3 - Android 4.1.28 | 6 | 2013-04-03 | PASS
TC040.4 | Test Logout | Samsung S3 - Android 4.1.29 | 6 | 2013-04-03 | PASS
TC41.1 | Test Create Bill (Customer) | Samsung S3 - Android 4.1.30 | 8 | 2013-04-03 | PASS
TC41.2 | Test Add Item to Bill (Customer) | Samsung S3 - Android 4.1.31 | 8 | 2013-04-03 | PASS
TC41.3 | Test Remove Item From Bill (Customer) | Samsung S3 - Android 4.1.32 | 9 | 2013-04-03 | PASS
TC41.4 | Test Delete Bill (Customer) | Samsung S3 - Android 4.1.33 | 9 | 2013-04-03 | PASS
TC42.1 | Test Create Bill (Restaurant) | Samsung S3 - Android 4.1.34 | 7 | 2013-04-03 | N/A
TC42.2 | Test Add Item to Bill (Restaurant) | Samsung S3 - Android 4.1.35 | 7 | 2013-04-03 | N/A
TC42.3 | Test Remove Item from Bill (Restaurant) | Samsung S3 - Android 4.1.36 | 7 | 2013-04-03 | N/A
TC42.4 | Test Delete Bill (Restaurant) | Samsung S3 - Android 4.1.37 | 7 | 2013-04-03 | N/A
TC192.1 | Test Create Table Page | Samsung S3 - Android 4.1.38 | 6 | 2013-04-03 | N/A
TC192.2 | Test Creating Incorrect Table Page | Samsung S3 - Android 4.1.39 | 6 | 2013-04-03 | N/A
TC192.3 | Test Edit Table Page | Samsung S3 - Android 4.1.40 | 6 | 2013-04-03 | N/A
TC192.4 | Test Incorrect Edit Table Page | Samsung S3 - Android 4.1.41 | 6 | 2013-04-03 | N/A
TC192.5 | Test NFC Link Page | Samsung S3 - Android 4.1.42 | 6 | 2013-04-03 | N/A
TC192.6 | Test Table Details Page | Samsung S3 - Android 4.1.43 | 6 | 2013-04-03 | N/A
TC192.7 | Test Delete Table Page | Samsung S3 - Android 4.1.44 | 6 | 2013-04-03 | N/A
TC279.1 | Test View Past Orders | Samsung S3 - Android 4.1.45 | 8 | 2013-04-03 | PASS
TC279.2 | Test Suggest an Order | Samsung S3 - Android 4.1.46 | 8 | 2013-04-03 | PASS

## Sprint9
Test ID | Title | Environment | Sprint | Test Date | Status | Notes
TC025.1 | Test Create Order | Google Chrome 25.0.1364.160 m | 6 | 2013-03-10 | FAIL | The system displays "Pick a Side" with the option "None" selected. You also only have the option to "Place Order" or hit the X. Place order seems misleading, it implies you cannot continue adding food. Should read "Add to Order"
TC026.1 | Test View Menu (Customer) | Google Chrome 25.0.1364.160 m | 6 | 2013-03-10 | PASS
TC026.2 | Test View Menu (Restaurant) | Google Chrome 25.0.1364.160 m | 6 | 2013-03-10 | FAIL | The expected result in step 2 is not correct. This test case needs to be updated. The restaurant sees a list of categories in the menu and possible new categories to add to the menu.
TC026.3 | Test View Menu (Administrator) | Google Chrome 25.0.1364.160 m | 6 | 2013-03-10 | FAIL | As discussed in the Sprint 9 meeting the admin user role should have the same rights as a developer. Need to updated system to reflect this.
TC026.4 | Test Search Menu (Customer) | Google Chrome 25.0.1364.160 m | 8 | 2013-03-10 | N/A | Cannot execute this test. These items are not in the DB. When you create them they still do not show up in the search, I would imagine this is because the indexer script needs to be run… Consider changing this TC to be more generic
TC026.5 | Test Search Menu (Restaurant) | Google Chrome 25.0.1364.160 m | 8 | 2013-03-10 | N/A | Cannot execute this test. These items are not in the DB. When you create them they still do not show up in the search, I would imagine this is because the indexer script needs to be run… Consider changing this TC to be more generic
TC026.6 | Test Search Menu (Administrator) | Google Chrome 25.0.1364.160 m | 8 | 2013-03-10 | N/A | Cannot execute this test. These items are not in the DB. When you create them they still do not show up in the search, I would imagine this is because the indexer script needs to be run… Consider changing this TC to be more generic
TC027.1 | Test Menu Editor Main Page | Google Chrome 25.0.1364.160 m | 6 | 2013-03-10 | PASS | Passes as a restaurant user. Do not see Menus list as Administrator unless admin is registered as a resto user which should not be necessary
TC027.2 | Test Category Management Page | Google Chrome 25.0.1364.160 m | 6 | 2013-03-10 | PASS | Passes as a restaurant user. Do not see Menus list as Administrator unless admin is registered as a resto user which should not be necessary
TC027.3 | Test Item Management Page | Google Chrome 25.0.1364.160 m | 6 | 2013-03-10 | FAIL | Cannot preform step 3. No way to edit this item using current flow described by test case. (Logged in as resto user)
TC027.4 | Test Menu Edit | Google Chrome 25.0.1364.160 m | 6 | 2013-03-10 | PASS | Passes as a restaurant user. Do not see Menus list as Administrator unless admin is registered as a resto user which should not be necessary
TC027.5 | Test Create Menu | Google Chrome 25.0.1364.160 m | 6 | 2013-03-10 | PASS | Passes as a restaurant user. Do not see Menus list as Administrator unless admin is registered as a resto user which should not be necessary
TC029.1 | Test Cancel Order | Google Chrome 25.0.1364.160 m | 6 | 2013-03-10 | FAIL | Expected result in step 3 does not happen. We no longer see the order in the list. Do not see Menus list as Administrator unless admin is registered as a resto user which should not be necessary
TC029.2 | Test Decline Order Item | Google Chrome 25.0.1364.160 m | 6 | 2013-03-10 | PASS | Do not see Menus list as Administrator unless admin is registered as a resto user which should not be necessary
TC029.3 | Test Accept Order Item | Google Chrome 25.0.1364.160 m | 6 | 2013-03-10 | FAIL | The order item for which you click "Accept" is set to Processing but all order items in the order are set to PENDING which should not happen.
TC034.1 | Test Create Service Request (Administrator) | Google Chrome 25.0.1364.160 m | 7 | 2013-03-10 | PASS | Do not see Menus list as Administrator unless admin is registered as a resto user which should not be necessary
TC034.2 | Test Create Service Request (Restaurant) | Google Chrome 25.0.1364.160 m | 7 | 2013-03-10 | PASS | Do not see Menus list as Administrator unless admin is registered as a resto user which should not be necessary
TC034.3 | Test Call Waiter (Customer) | Google Chrome 25.0.1364.160 m | 7 | 2013-03-10 | FAIL | Functionality works but expected result #2 does not occure instead we are displayed the login page
TC034.4 | Test Edit Service Request (Restaurant) | Google Chrome 25.0.1364.160 m | 7 | 2013-03-10 | PASS
TC034.5 | Test Edit Service Request (Administrator) | Google Chrome 25.0.1364.160 m | 7 | 2013-03-10 | FAIL | Status does not display words it displays the number. Setting status to 0 does not set the request to closed. Do not see Menus list as Administrator unless admin is registered as a resto user which should not be necessary
TC034.6 | Test Cancel Service Request | Google Chrome 25.0.1364.160 m | 7 | 2013-03-10 | PASS
TC034.7 | Test Complete Service Request | Google Chrome 25.0.1364.160 m | 7 | 2013-03-10 | PASS
TC035.3 | Test Update Customer Settings | Google Chrome 25.0.1364.160 m | 9 | 2013-03-10 | FAIL | Customer does not have the ability to see the User link. Tets case missing the name of the link.
TC039.1 | Test Leave Review | Google Chrome 25.0.1364.160 m | 8 | 2013-03-10 | FAIL | The user does not see the Profile link
TC039.2 | Test View Review | Google Chrome 25.0.1364.160 m | 8 | 2013-03-10 | PASS | hardcoded review in the db to be able to test this
TC040.1 | Test Login With Non-Existent User | Google Chrome 25.0.1364.160 m | 6 | 2013-03-10 | PASS
TC040.2 | Test Create New User | Google Chrome 25.0.1364.160 m | 6 | 2013-03-10 | PASS
TC040.3 | Test Login With Existent User | Google Chrome 25.0.1364.160 m | 6 | 2013-03-10 | FAIL | password should be case senstaive but it is not so the test fails at step 2
TC040.4 | Test Logout | Google Chrome 25.0.1364.160 m | 6 | 2013-03-10 | PASS
TC41.1 | Test Create Bill (Customer) | Google Chrome 25.0.1364.160 m | 8 | 2013-03-10 | FAIL | user does not see manage bills link.
TC41.2 | Test Add Item to Bill (Customer) | Google Chrome 25.0.1364.160 m | 8 | 2013-03-10 | FAIL | cannot manage bills as a customer
TC41.3 | Test Remove Item From Bill (Customer) | Google Chrome 25.0.1364.160 m | 9 | 2013-03-10 | FAIL | cannot manage bills as a customer
TC41.4 | Test Delete Bill (Customer) | Google Chrome 25.0.1364.160 m | 9 | 2013-03-10 | FAIL | cannot manage bills as a customer
TC42.1 | Test Create Bill (Restaurant) | Google Chrome 25.0.1364.160 m | 7 | 2013-03-10 | PASS
TC42.2 | Test Add Item to Bill (Restaurant) | Google Chrome 25.0.1364.160 m | 7 | 2013-03-10 | PASS
TC42.3 | Test Remove Item from Bill (Restaurant) | Google Chrome 25.0.1364.160 m | 7 | 2013-03-10 | PASS
TC42.4 | Test Delete Bill (Restaurant) | Google Chrome 25.0.1364.160 m | 7 | 2013-03-10 | FAIL | there is no delete bill button displayed.
TC192.1 | Test Create Table Page | Google Chrome 25.0.1364.160 m | 6 | 2013-03-10 | PASS | Passes as a restaurant user. Do not see Menus list as Administrator unless admin is registered as a resto user which should not be necessary
TC192.2 | Test Creating Incorrect Table Page | Google Chrome 25.0.1364.160 m | 6 | 2013-03-10 | PASS | Passes as a restaurant user. Do not see Menus list as Administrator unless admin is registered as a resto user which should not be necessary
TC192.3 | Test Edit Table Page | Google Chrome 25.0.1364.160 m | 6 | 2013-03-10 | PASS | Passes as a restaurant user. Do not see Menus list as Administrator unless admin is registered as a resto user which should not be necessary
TC192.4 | Test Incorrect Edit Table Page | Google Chrome 25.0.1364.160 m | 6 | 2013-03-10 | PASS | Passes as a restaurant user. Do not see Menus list as Administrator unless admin is registered as a resto user which should not be necessary
TC192.5 | Test NFC Link Page | Google Chrome 25.0.1364.160 m | 6 | 2013-03-10 | PASS | Passes as a restaurant user. Do not see Menus list as Administrator unless admin is registered as a resto user which should not be necessary
TC192.6 | Test Table Details Page | Google Chrome 25.0.1364.160 m | 6 | 2013-03-10 | PASS | Passes as a restaurant user. Do not see Menus list as Administrator unless admin is registered as a resto user which should not be necessary
TC192.7 | Test Delete Table Page | Google Chrome 25.0.1364.160 m | 6 | 2013-03-10 | FAIL | internal server error occures as restaurant user and Admin user.
TC279.1 | Test View Past Orders | Google Chrome 25.0.1364.160 m | 8 | 2013-03-10 | FAIL | user cannot access profile page
TC279.2 | Test Suggest an Order | Google Chrome 25.0.1364.160 m | 8 | 2013-03-10 | FAIL | server error in application is displayed

## Sprint8
Test ID | Title | Environment | Sprint | Test Date | Status | Notes
TC025.1 | Test Create Order | Google Chrome 24.0.1312.57 m | 6 | 2013-02-24 | PASS
TC026.1 | Test View Menu (Customer) | Google Chrome 24.0.1312.57 m | 6 | 2013-02-24 | PASS
TC026.2 | Test View Menu (Restaurant) | Google Chrome 24.0.1312.57 m | 6 | 2013-02-24 | FAIL | Displays administrative view instead of user menu view
TC026.3 | Test View Menu (Administrator) | Google Chrome 24.0.1312.57 m | 6 | 2013-02-24 | FAIL | Does not have capability to view menus as an administrator
TC026.4 | Test Search Menu (Customer) | Google Chrome 24.0.1312.57 m | 8 | 2013-02-24 | PASS
TC026.5 | Test Search Menu (Restaurant) | Google Chrome 24.0.1312.57 m | 8 | 2013-02-24 | FAIL | Restaurant search fails because they have not tapped into a table
TC026.6 | Test Search Menu (Administrator) | Google Chrome 24.0.1312.57 m | 8 | 2013-02-24 | FAIL | Fails due to not having tapped into a table
TC027.1 | Test Menu Editor Main Page | Google Chrome 24.0.1312.57 m | 6 | 2013-02-24 | PASS
TC027.2 | Test Category Management Page | Google Chrome 24.0.1312.57 m | 6 | 2013-02-24 | PASS
TC027.3 | Test Item Management Page | Google Chrome 24.0.1312.57 m | 6 | 2013-02-24 | FAIL | Cannot edit items from their list in categories
TC027.4 | Test Menu Edit | Google Chrome 24.0.1312.57 m | 6 | 2013-02-24 | FAIL | Cannot remove categories from the menu
TC027.5 | Test Create Menu | Google Chrome 24.0.1312.57 m | 6 | 2013-02-24 | PASS
TC029.1 | Test Cancel Order | Google Chrome 24.0.1312.57 m | 6 | 2013-02-24 | PASS
TC029.2 | Test Decline Order Item | Google Chrome 24.0.1312.57 m | 6 | 2013-02-24 | PASS
TC029.3 | Test Accept Order Item | Google Chrome 24.0.1312.57 m | 6 | 2013-02-24 | PASS
TC034.1 | Test Create Service Request (Administrator) | Google Chrome 24.0.1312.57 m | 7 | 2013-02-24 | PASS
TC034.2 | Test Create Service Request (Restaurant) | Google Chrome 24.0.1312.57 m | 7 | 2013-02-24 | PASS
TC034.3 | Test Call Waiter (Customer) | Google Chrome 24.0.1312.57 m | 7 | 2013-02-24 | FAIL | Service request action happens as expected except that user is prompted for login. This should not happen.
TC034.4 | Test Edit Service Request (Restaurant) | Google Chrome 24.0.1312.57 m | 7 | 2013-02-24 | PASS
TC034.5 | Test Edit Service Request (Administrator) | Google Chrome 24.0.1312.57 m | 7 | 2013-02-24 | FAIL | Service requests are not visible to admin
TC034.6 | Test Cancel Service Request | Google Chrome 24.0.1312.57 m | 7 | 2013-02-24 | PASS
TC034.7 | Test Close Service Request | Google Chrome 24.0.1312.57 m | 7 | 2013-02-24 | PASS
TC039.1 | Test Leave Review | Google Chrome 24.0.1312.57 m | 8 | 2013-02-24 | FAIL | Code not merged in yet. Cannot test.
TC039.2 | Test View Review | Google Chrome 24.0.1312.57 m | 8 | 2013-02-24 | FAIL | Code not merged in yet. Cannot test.
TC040.1 | Test Login With Non-Existent User | Google Chrome 24.0.1312.57 m | 6 | 2013-02-24 | PASS
TC040.2 | Test Create New User | Google Chrome 24.0.1312.57 m | 6 | 2013-02-24 | PASS
TC040.3 | Test Login With Existent User | Google Chrome 24.0.1312.57 m | 6 | 2013-02-24 | FAIL | Password should be case sensitive. Logs user in with incorrect password.
TC040.4 | Test Logout | Google Chrome 24.0.1312.57 m | 6 | 2013-02-24 | PASS
TC41.1 | Test Create Bill (Customer) | Google Chrome 24.0.1312.57 m | 8 | 2013-02-24 | FAIL | Fails at step 3. No bill is displayed.
TC41.2 | Test Add Item to Bill (Customer) | Google Chrome 24.0.1312.57 m | 8 | 2013-02-24 | FAIL | Precondition of TC41.1 fails
TC42.3 | Test Remove Item from Bill (Customer) | Google Chrome 24.0.1312.57 m | 8 | 2013-02-24 | FAIL | Precondition of TC41.2 fails
TC42.4 | Test Delete Bill (Customer) | Google Chrome 24.0.1312.57 m | 8 | 2013-02-24 | FAIL | Precondition of TC41.2 fails
TC42.1 | Test Create Bill (Restaurant) | Google Chrome 24.0.1312.57 m | 7 | 2013-02-24 | PASS
TC42.2 | Test Add Item to Bill (Restaurant) | Google Chrome 24.0.1312.57 m | 7 | 2013-02-24 | PASS
TC42.3 | Test Remove Item from Bill (Restaurant) | Google Chrome 24.0.1312.57 m | 7 | 2013-02-24 | PASS
TC42.4 | Test Delete Bill (Restaurant) | Google Chrome 24.0.1312.57 m | 7 | 2013-02-24 | PASS
TC192.1 | Test Create Table Page | Google Chrome 24.0.1312.57 m | 6 | 2013-02-24 | PASS
TC192.2 | Test Creating Incorrect Table Page | Google Chrome 24.0.1312.57 m | 6 | 2013-02-24 | FAIL | System crashes instead of displaying error message
TC192.3 | Test Edit Table Page | Google Chrome 24.0.1312.57 m | 6 | 2013-02-24 | PASS
TC192.4 | Test Incorrect Edit Table Page | Google Chrome 24.0.1312.57 m | 6 | 2013-02-24 | FAIL | Saves even without a name. Should have a name.
TC192.5 | Test NFC Link Page | Google Chrome 24.0.1312.57 m | 6 | 2013-02-24 | PASS
TC192.6 | Test Table Details Page | Google Chrome 24.0.1312.57 m | 6 | 2013-02-24 | PASS
TC192.7 | Test Delete Table Page | Google Chrome 24.0.1312.57 m | 6 | 2013-02-24 | FAIL | Table is still shown on the list.
TC279.1 | Test View Past Orders | Google Chrome 24.0.1312.57 m | 8 | 2013-02-24 | FAIL | Code not merged in yet. Cannot test.
TC279.2 | Test Suggest an Order | Google Chrome 24.0.1312.57 m | 8 | 2013-02-24 | FAIL | Code not merged in yet. Cannot test.

## Sprint7
Test ID | Title | Environment | Sprint | Test Date | Status | Notes
TC025.1 | Test Create Order | Google Chrome 24.0.1312.57 m | 6 | 2013-02-10 | FAIL | - Doesn't work for a a user with role customer. |  | FAIL
TC026.1 | Test View Menu (Customer) | Google Chrome 24.0.1312.57 m | 6 | 2013-02-10 | FAIL | - Menu list is not exclusive to the restaurant where the user is signed in. - Intervention in the database is required to make menus categories and items visible. | ` | PASS
TC026.2 | Test View Menu (Restaurant) | Google Chrome 24.0.1312.57 m | 6 | 2013-02-10 | FAIL | - Menu list is not exclusive to the restaurants associated to the user. - The option to order food should not be available to restaurant users.
TC026.3 | Test View Menu (Administrator) | Google Chrome 24.0.1312.57 m | 6 | 2013-02-10 | PASS
TC027.1 | Test Menu Editor Main Page | Google Chrome 24.0.1312.57 m | 6 | 2013-02-10 | FAIL | - All the current menus are not displayed.
TC027.2 | Test Category Management Page | Google Chrome 24.0.1312.57 m | 6 | 2013-02-10 | PASS
TC027.3 | Test Item Management Page | Google Chrome 24.0.1312.57 m | 6 | 2013-02-10 | FAIL | - Option to edit an item is unavailable.
TC027.4 | Test Menu Edit | Google Chrome 24.0.1312.57 m | 6 | 2013-02-10 | FAIL | - Category cannot be removed.
TC027.5 | Test Create Menu | Google Chrome 24.0.1312.57 m | 6 | 2013-02-10 | PASS
TC029.1 | Test Cancel Order | Google Chrome 24.0.1312.57 m | 6 | 2013-02-10 | FAIL | - Option to cancel order is not visible
TC029.2 | Test Decline Order Item | Google Chrome 24.0.1312.57 m | 6 | 2013-02-10 | PASS
TC029.3 | Test Accept Order Item | Google Chrome 24.0.1312.57 m | 6 | 2013-02-10 | FAIL | - Order item status not visible - No indication that the order was successfully accepted provided.
TC034.1 | Test Create Service Request (Administrator) | Google Chrome 24.0.1312.57 m | 7 | 2013-02-10 | PASS
TC034.2 | Test Create Service Request (Restaurant) | Google Chrome 24.0.1312.57 m | 7 | 2013-02-10 | PASS
TC034.3 | Test Call Waiter (Customer) | Google Chrome 24.0.1312.57 m | 7 | 2013-02-10 | PASS
TC034.4 | Test Edit Service Request (Restaurant) | Google Chrome 24.0.1312.57 m | 7 | 2013-02-10 | PASS
TC034.5 | Test Edit Service Request (Administrator) | Google Chrome 24.0.1312.57 m | 7 | 2013-02-10 | PASS
TC034.6 | Test Cancel Service Request | Google Chrome 24.0.1312.57 m | 7 | 2013-02-10 | PASS
TC034.7 | Test Close Service Request | Google Chrome 24.0.1312.57 m | 7 | 2013-02-10 | PASS
TC040.1 | Test Login With Non-Existent User | Google Chrome 24.0.1312.57 m | 6 | 2013-02-10 | PASS
TC040.2 | Test Create New User | Google Chrome 24.0.1312.57 m | 6 | 2013-02-10 | PASS |  |  | TBD
TC040.3 | Test Login With Existent User | Google Chrome 24.0.1312.57 m | 6 | 2013-02-10 | FAIL | - Password is not case sensitive |  | PASS
TC040.4 | Test Logout | Google Chrome 24.0.1312.57 m | 6 | 2013-02-10 | PASS |  |  | FAIL
TC42.1 | Test Create Bill (Restaurant) | Google Chrome 24.0.1312.57 m | 7 | 2013-02-10 | PASS
TC42.2 | Test Add Item to Bill (Restaurant) | Google Chrome 24.0.1312.57 m | 7 | 2013-02-10 | PASS
TC42.3 | Test Remove Item from Bill (Restaurant) | Google Chrome 24.0.1312.57 m | 7 | 2013-02-10 | PASS
TC42.4 | Test Delete Bill (Restaurant) | Google Chrome 24.0.1312.57 m | 7 | 2013-02-10 | PASS
TC192.1 | Test Create Table Page | Google Chrome 24.0.1312.57 m | 6 | 2013-02-10 | PASS
TC192.2 | Test Creating Incorrect Table Page | Google Chrome 24.0.1312.57 m | 6 | 2013-02-10 | FAIL | - No error message is displayed.
TC192.3 | Test Edit Table Page | Google Chrome 24.0.1312.57 m | 6 | 2013-02-10 | PASS
TC192.4 | Test Incorrect Edit Table Page | Google Chrome 24.0.1312.57 m | 6 | 2013-02-10 | FAIL | - No error message is displayed.
TC192.5 | Test NFC Link Page | Google Chrome 24.0.1312.57 m | 6 | 2013-02-10 | FAIL | - Error is thrown when table isn’t associated to a restaurant
TC192.6 | Test Table Details Page | Google Chrome 24.0.1312.57 m | 6 | 2013-02-10 | PASS
TC192.7 | Test Delete Table Page | Google Chrome 24.0.1312.57 m | 6 | 2013-02-10 | PASS

## Sprint6
Test ID | Title | Environment | Sprint | Test Date | Status | Notes
TC025.1 | Test Create Order | Google Chrome 24.0.1312.57 m | 6 | 2013-01-27 | FAIL | - Doesn't work for a regular user, don't know if this was intended |  | FAIL
TC026.1 | Test View Menu (Customer) | Google Chrome 24.0.1312.57 m | 6 | 2013-01-27 | FAIL | - Can't finalize the order, unless that's expected | ` | PASS
TC026.2 | Test View Menu (Restaurant) | Google Chrome 24.0.1312.57 m | 6 | 2013-01-27 | FAIL | - The user should not be able to see the remove buttons.
TC026.3 | Test View Menu (Administrator) | Google Chrome 24.0.1312.57 m | 6 | 2013-01-27 | PASS
TC027.1 | Test Menu Editor Main Page | Google Chrome 24.0.1312.57 m | 6 | 2013-01-28 | PASS
TC027.2 | Test Category Management Page | Google Chrome 24.0.1312.57 m | 6 | 2013-01-28 | PASS | - On site, it's + New Category. In test case, it specifies "Create New Category"
TC027.3 | Test Item Management Page | Google Chrome 24.0.1312.57 m | 6 | 2013-01-28 | PASS
TC027.4 | Test Menu Edit | Google Chrome 24.0.1312.57 m | 6 | 2013-01-28 | FAIL | - Can't remove a category
TC027.5 | Test Create Menu | Google Chrome 24.0.1312.57 m | 6 | 2013-01-28 | PASS
TC029.1 | Test Cancel Order | Google Chrome 24.0.1312.57 m | 6 | 2013-01-28 | FAIL | - Can't view orders
TC029.2 | Test Decline Order Item | Google Chrome 24.0.1312.57 m | 6 | 2013-01-28 | FAIL | - Can't view orders
TC029.3 | Test Accept Order Item | Google Chrome 24.0.1312.57 m | 6 | 2013-01-28 | FAIL | - Can't view orders
TC040.1 | Test Login With Non-Existent User | Google Chrome 24.0.1312.57 m | 6 | 2013-01-27 | PASS
TC040.2 | Test Create New User | Google Chrome 24.0.1312.57 m | 6 | 2013-01-27 | PASS |  |  | TBD
TC040.3 | Test Login With Existent User | Google Chrome 24.0.1312.57 m | 6 | 2013-01-27 | FAIL | - Not case sensitive for user name or for password i.e. can write testinguser / testing |  | PASS
TC040.4 | Test Logout | Google Chrome 24.0.1312.57 m | 6 | 2013-01-27 | PASS |  |  | FAIL
TC192.1 | Test Create Table Page | Google Chrome 24.0.1312.57 m | 6 | 2013-01-28 | PASS
TC192.2 | Test Creating Incorrect Table Page | Google Chrome 24.0.1312.57 m | 6 | 2013-01-28 | FAIL | - Can create a table with no information, no error message
TC192.3 | Test Edit Table Page | Google Chrome 24.0.1312.57 m | 6 | 2013-01-28 | PASS
TC192.4 | Test Incorrect Edit Table Page | Google Chrome 24.0.1312.57 m | 6 | 2013-01-28 | FAIL | - Can create a table with no name, no error message appears
TC192.5 | Test NFC Link Page | Google Chrome 24.0.1312.57 m | 6 | 2013-01-28 | FAIL | - Can click on NFC link to tables that are not linked to a restaurant, which results in an error
TC192.6 | Test Table Details Page | Google Chrome 24.0.1312.57 m | 6 | 2013-01-28 | PASS
TC192.7 | Test Delete Table Page | Google Chrome 24.0.1312.57 m | 6 | 2013-01-28 | PASS

## Status Types (hidden)
STATUS TYPES
PASS
FAIL
N/A